East Area Parks				Greenbank Park Greenflag Work

| Work Priority | Location | Who / Funding | Target Date |
| --- | --- | --- | --- |
| New Archway on entrance | Main Entrance off Mount road | Groundwork landscapes/ Capital or Cash Grant | May 2010 |
| Install Kissing Gates on each Entrance | Whole Park | Groundwork landscape/ Capital | May 2010 |
| Install new Entrance Signs | Manor Road & Baslow Ave entrances | Sign it up / GreenFlag Funding/Capital | May 2010 |
| Resurface tarmac pathways | Main entrance of Mount Road | Manchester Contracts Andy Gay / Capital | April 2010 |
| Clean up hedgerow & mulch | Privet hedge surrounding park | Grounds Maintenance | March 2010 Completed |
| Seed areas on left hand side of entrance to park | Main Entrance off Mount road | Grounds Maintenance | April 2010 Completed |
| Clean up & remove graffiti from Dog bins | Whole Park | Richard Eccles | April 2010 |
| Paint up Wooden Benches black | Next to Bowling Greens | Paul & Ian | March 2010 |
| Paint up Gateway ( currently closed off) | Next to Bowling Greens | Paul & Ian | March 2010 |
| Take out tarmac pathway & soil over | Next to Bowling Greens | Groundwork/Rapid team | May 2010 |
| Take out section of Shrubbery & soil & seed up | Entrance next to Bowling Greens | Ground Maintenance | March 2010 Completed |
| Fencing Panel install on Baslow Ave | Baslow Ave | Groundwork | May 2010 |
| Cut back & tidy up around bottom of Berberis Shrub bed | Corner bed in centre of park | Grounds Maintenance | March 2010 Completed |
| Cut back & tidy shrubbery next to Bowling Greens | Corner bed next two Bowling Greens | Grounds Maintenance | March 2010 Completed |
| Install Natural Playbuilder Equipment | Link park to fields | Manchester Contracts | May 2010 Completed |
| Weed & tidy up & mulch Shrub borders | Along Manor Rd hedgerow | Grounds Maintenance | March 2010 Completed |
| Install Bird Boxes in trees | Whole Park | Richard Eccles | March 2010 |
| Planting of trees x 10 | Old Bowling Green site | Alan & Carl / Capital | November 2010 |
| Install Noticeboard on Entrance | Main Entrance off Mount Road | Sign it up / Greenflag funding | May 2010 |
| 4 x Park Benches | Main pathway | Sign it up / Capital | May 2010 |
| Install Lectern in park | Entrance off manor Road | Sign it up /Capital | May 2010 |
| Fence off section in park off Baslow Ave | Baslow Ave area at the end of the houses | Greenwork /Capital | May 2010 |
| Take out seedling trees along fence line | Houses that come off Baslow Ave | Grounds Maintenance | March 2010 |
| Take out section of shrubbery next to entrance on Manor Rd | Entrance off Manor Road | Grounds Maintenance | March 2010 Completed |